## ProjectDetails
Unicourt APP
Estimates Prepared By
Estimates Reviewed By
Estimates Approved By
References

## Leave plan
Release start date: 01/09/2023
Release end date: 30/11/2023
No.of days available in release (excluding weekend and public holidays) | 20 days
No. of QA resources available | 8
QA Name | No.of leaves | Total available days | No. of Available hrs(Available days*6)
JQA1 | 2 | 18
JQA2 | 3 | 18
JQA3 | 1 | 20
JQA4 | 0 | 21
JQA5 | 2 | 19
JQA6 | 2 | 19
SQA1 | 3 | 18
SQA2 | 3 | 18

## Estimation
SL.no | Story/bug id/task | Resource for manual testing | Resource for automation testing | Resource for performance testing | Requirement Analysis | Test case preparation | Testcase review | Testdata preparation | Testplan design | Testplan review | Test Execution | Manual Regression testing | Automated testcase preparation | Automated testcase review | Automated test data preparation | Automated test environment setup | Automation script preparation | Automation script review and review incorporation | Automation script execution and report analysis | Automation Regression and script fix | Performance testcase preparation | Performance testdata preparation | Performance test execution | Performance bug verification and reexecution | Regression checklist update | Traceability matrix update | Grand total
1 | UCT_1001: Webportal and User Authentication | JQA1 | JQA2 | NA | 3 | 5 | 1 | 2 | NA | NA | 5 | NA | 2 | 1 | 1 | 4 | 20 | 2 | 3 | 5 | NA | NA | NA | NA | 0.5 | 0.5
1 | UCT_1001: User Role | JQA3 | JQA3 | NA | 2 | 2 | 1 | 2 | NA | NA | 3 | NA | 1 | 1 | 1 | NA | 20 | 2 | 3 | 5 | NA | NA | NA | NA | 0.5 | 0.5
1 | UCT_1001: Authentication | JQA4 | JQA5 | NA | 3 | 3 | 1 | 2 | NA | NA | 5 | NA | 1 | 1 | 2 | NA | 32 | 2 | 3 | 10 | NA | NA | NA | NA | 0.5 | 0.5
1 | Regression | JQA6 | JQA5 | NA | NA | NA | NA | 3 | NA | NA | NA | 20 | NA | NA | 5 | 4 | NA | NA | 5 | 10 | NA | NA | NA | NA | NA | NA
1 | Performance | NA | NA | SQA1, SQA2 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 3 | 5 | 50 | 30 | NA | NA
| Testplan | Lead | NA | NA | NA | NA | NA | NA | 24 | 10 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
| GRAND TOTAL EFFORT IN PERSON HOURS |  |  |  | 8 | 10 | 3 | 9 | 24 | 10 | 13 | 20 | 4 | 3 | 9 | 8 | 72 | 6 | 14 | 30 | 3 | 5 | 50 | 30 | 1.5 | 1.5 | 334